## Sheet1
in all data tables | set the table for responsiveness
Home page
http://samarthya.16mb.com/version1/ | Login problem when resized | Done
forgot password link problem - closing on 2 clicks
| courses link - navigating to wrong page | Done
| contact us link - navigating to wrong page | Done
| login link - navigating to wrong page | Done
| home link - navigating to wrong page | Done
Reports page
http://samarthya.16mb.com/version1/reports.php | filters not implemented - get distinct values from backend - implement on the column headers
remove "staff id" coulmn, and add "status" column
filters for - state, course name and designation, status
| download data option | NA
| remove extra space after table rows | Done
| remove the bottom text | Done
arrange login popup in the same page
arrange signup in the same page
in type of test - get the values of "Assessment" only
Contact us page
http://samarthya.16mb.com/version1/contact.php | remove unwanted links in the top navigation bar
change top navigation bar links as reports page navigation
send a mail to the given mail ids on clicking "Post Message" button
signup link in the bottom is not working
arrange login popup in the same page
arrange signup in the same page
Courses page
http://samarthya.16mb.com/version1/courses.php
arrange login popup in the same page
arrange signup in the same page
user roman letters for course numbers
Signup | issue in signup page
user-landing.php | activate "Go to Module" link in all the courses
use roman letters for course numbers
Admin Panel
delete home link, by default show "user-details.php" when admin logs in
Dele option in user-details.php to delete if necessary

## Version-1- sequence
Course-I
Pretest
| Details/Module | User has to see all the youtube links and has to download all the PDFs
| Posttest | User has to pass the test by getting 60% marks
If Fails - direct the user to take modules of Course-I
Course-II
| Pretest | Should not be able to take this test if the user has not passed Posttest of Course-I
| Details/Module | User has to see all the youtube links and has to download all the PDFs
| Posttest | User has to pass the test by getting 60% marks
If Fails - direct the user to take modules of Course-II
Course-III
| Pretest | Should not be able to take this test if the user has not passed Posttest of Course-II
| Details/Module | User has to see all the youtube links and has to download all the PDFs
| Posttest | User has to pass the test by getting 60% marks
If Fails - direct the user to take modules of Course-III
Course-IV
| Pretest | Should not be able to take this test if the user has not passed Posttest of Course-III
| Details/Module | User has to see all the youtube links and has to download all the PDFs
| Posttest | User has to pass the test by getting 60% marks
If Fails - direct the user to take modules of Course-IV
Certification Test
Should not be able to take this test if the user has not passed Posttest of Course-IV